## BurndownChart
BURNDOWN CHART - GROUP #91
Daily meeting record | Days | Goal | Done | Goal velocity | Remaining | Hours Spent
Meeting 1 (27/11) | 0 | 0 | 0 | 25 | 25 | 2
| 1 | 1 | 1 | 24 | 24 | 4
| 2 | 2 | 1 | 23 | 23 | 8
Meeting 2 (30/11) | 3 | 3 | 2 | 22 | 21 | 8
Meeting 3 (01/12) | 4 | 4 | 1 | 21 | 20 | 10
| 5 | 5 | 0 | 20 | 20 | 12
Meeting 4 (03/12) | 6 | 6 | 1 | 19 | 19 | 11
| 7 | 7 | 1 | 18 | 18 | 12
Meeting 5 (05/12) | 8 | 8 | 0 | 17 | 18 | 14
| 9 | 9 | 1 | 16 | 17 | 16
| 10 | 10 | 2 | 15 | 15 | 16
Meeting 6 (08/12) | 11 | 11 | 1 | 14 | 14 | 18
| 12 | 12 | 1 | 13 | 13 | 20
Meeting 7 (10/12) | 13 | 13 | 1 | 12 | 12 | 22
| 14 | 14 | 2 | 11 | 10 | 24
Meeting 8 (12/12) | 15 | 15 | 1 | 10 | 9 | 26
| 16 | 16 | 0 | 9 | 9 | 28
| 17 | 17 | 0 | 8 | 9 | 28
Meeting 9 (15/12) | 18 | 18 | 1 | 7 | 8 | 30
Meeting 10 (16/12) | 19 | 19 | 0 | 6 | 8 | 32
Meeting 11 (17/12) | 20 | 20 | 3 | 5 | 5 | 34
Meeting 12 (18/12) | 21 | 21 | 0 | 4 | 5 | 36
Meeting 13 (19/12) | 22 | 22 | 0 | 3 | 5 | 38
| 23 | 23 |  | 2 | 5
| 24 | 24 |  | 1 | 5
| 25 | 25 |  | 0 | 5
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert daily meeting record. Can be Yes/no and the link to Git
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update according with the days of the sprint
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update according with the real done items